## Sheet1
DJTC ID | DJTC DATE | PRD NO | PROJECT | OPERATION | PRODUCT | WBS ELEMENT | MATERIAL NO | WORK CENTER | SHIFT | SUPERVISOR | SHOP | PS NO PS NAME | END SHIFT REMARK | Grade | AUDITED BY | STATUS
757686 | 12/05/2025 | 1000140958 | HAZIRA-DO | 0090 - Drilling by Portable machine | STRUCTURA | MNMBF3-67504 | DUBF3504038GR-4-1 : BF#3 - GIRDER-GR-4-1 | BB030 | Shift A | 20018913 - Kishor Patel | B | 20043052 - Krunalkumar Bharucha | checked and found ok | 10 | 20018913 - Kishor Patel | Approved
757710 | 12/05/2025 | 1000140030 | 21034A | 1030 - Y-Piece Fit-up | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB160 | Shift A | 20077565 - Jaimin Patel | B (Expansion) | 20064595 - Sandipkumar Balwantbhai Patel | Found ok | 10 | 20077565 - Jaimin Patel | In Review
757687 | 12/05/2025 | 1000140503 | HAZIRA-DO | 0090 - Drilling by Portable machine | STRUCTURA | MNMBF3-67507 | DUBF3517005RBR-8X : BF#3 - RAFTER BRACING-RBR-8X | BB030 | Shift A | 20018913 - Kishor Patel | B | 20051566 - Pareshkumar Punambhai Solanki | drilling checked and found ok | 10 | 20018913 - Kishor Patel | Approved
757720 | 12/05/2025 | 1000140895 | 21034G | 0020 - ATCP Line In Shop C | PANEL_LMB | 21034G-122000121 | SF21034G122000121L : DRG NO: 12200-0121L For 21034G | BC020 | Shift A | 20012636 - Chandan Jangid | C2 | 20054728 - Pareshkumar Ravjibhai Vankar | Found ok | 10 | 20012636 - Chandan Jangid | Pending
757691 | 12/05/2025 | 1000141327 | HAZIRA-DO | 0010 - Marking | STRUCTURA | MNMBF3-67509 | SFMNM6750925FLMAYB : Floor Beam-Shop B(0525) | BB010 | Shift A | 20018913 - Kishor Patel | B | 20062399 - Rajeshkumar Chhaganbhai Luhariya | punching checked, material code punching line not proper,same informed to workmen and corrected, checked and found ok. | 8 | 20018913 - Kishor Patel | Approved
757713 | 12/05/2025 | 1000140030 | 21034A | 1040 - Y-Piece welding | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB240 | Shift B | 20077565 - Jaimin Patel | B (Expansion) | 20036768 - Chintankumar Prajapati | Found ok | 10 | 20077565 - Jaimin Patel | In Review
757690 | 12/05/2025 | 1000140574 | HAZIRA-DO | 0160 - Dimension check, WV, Support removal and | STRUCTURA | MNMBF3-67517 | DUBF367517005RB-7 : BF#3 - RAFTER BEAM-RB-7 | BA110 | Shift A | 20018913 - Kishor Patel | B | 20063324 - Hemantkumar Ganeshbhai Luhar | visual point given, same corrected and found ok | 10 | 20018913 - Kishor Patel | Approved
757720 | 12/05/2025 | 1000140895 | 21034G | 0020 - ATCP Line In Shop C | PANEL_LMB | 21034G-122000121 | SF21034G122000121L : DRG NO: 12200-0121L For 21034G | BC020 | Shift A | 20012636 - Chandan Jangid | C2 | 20054771 - Pareshbhai Ranchhodbhai Machhi | Found ok | 10 | 20012636 - Chandan Jangid | Pending
757692 | 12/05/2025 | 1000140361 | 1724 | 0080 - Mark no (16 + 18) & Assy fitup | PIPINGLMB | 1724-NTKG05-13400 | DU1724M4411321210 : PSH DESUPERHEATER | BB025 | Shift A | 20012505 - Yogendra Kumar Gupta | B | 20064290 - Rajendrasinh Arjunsinh Parmar | Spacer and RIng Fitup orientation checked and found ok, But Punching not visible properly on Job and same was corrected by workmen | 9 | 20012505 - Yogendra Kumar Gupta | Approved
757724 | 12/05/2025 | 1000140904 | 21034H | 0050 - MPM 20T WELDING -MPM1 | PANEL_LMB | 21034H-122000201 | SF21034H122000201L : DRG NO: 12200-0201L For 21034H | BC060 | Shift A | 20012636 - Chandan Jangid | C2 | 20051570 - Hiteshbhai Pravinbhai Makwana | Found ok | 10 | 20012636 - Chandan Jangid | In Review
757693 | 12/05/2025 | 1000140365 | 1724 | 0110 - Mark no (17 + 19) & Assy welding | PIPINGLMB | 1724-NTTD04-13400 | DU17242169667-0040 : PSH DESUPERHEATER | BB030 | Shift A | 20012505 - Yogendra Kumar Gupta | B | 20021399 - Dhavalkumar Patel | Spray Nozzle Spacer welding checked and found ok, Feedback given for efficiency improvement. | 10 | 20012505 - Yogendra Kumar Gupta | Approved
757721 | 12/05/2025 | 1000140904 | 21034H | 0010 - Shot Blasting of tubes | PANEL_LMB | 21034H-122000201 | SF21034H122000201L : DRG NO: 12200-0201L For 21034H | BC010 | Shift A | 20012636 - Chandan Jangid | C2 | 20074158 - Hitendrasinh Mahida | Found ok | 10 | 20012636 - Chandan Jangid | In Review
757692 | 12/05/2025 | 1000140361 | 1724 | 0080 - Mark no (16 + 18) & Assy fitup | PIPINGLMB | 1724-NTKG05-13400 | DU1724M4411321210 : PSH DESUPERHEATER | BB025 | Shift A | 20012505 - Yogendra Kumar Gupta | B | 20076208 - Jigneshkumar Dilipkumar Patel | Spacer and RIng Fitup orientation checked and found ok, But Punching not visible properly on Job and same was corrected by workmen | 9 | 20012505 - Yogendra Kumar Gupta | Approved
757740 | 12/05/2025 | 1000140893 | 21034H | 0070 - Squeezing And Sizing | COIL_LMB | 21034H-152000101 | SF21034H152000101 : WBS :15200-0101 (ESL) for 21034H | BF040 | Shift A | 20379356 - Ariwala Dhruval | F | 20054750 - Ankitkumar Jayantilal Patel | Found Ok. | 10 | 20379356 - Ariwala Dhruval | Approved
757695 | 12/05/2025 | 1000140359 | 1724 | 0100 - Welding of Reinforcing Pad | PIPINGLMB | 1724-NTKG05-13400 | DU1724M4411321117 : LINER PIPE | BB030 | Shift A | 20012505 - Yogendra Kumar Gupta | B | 20019427 - Gaurav | A/F welding post heating time not written on pipe, Asked to welder and same was written by welder. | 10 | 20012505 - Yogendra Kumar Gupta | Approved
757746 | 12/05/2025 | 1000139802 | 13022A | 0080 - Butt Joint (Auto-Tig) | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BF070 | Shift A | 20379356 - Ariwala Dhruval | F | 20063326 - Rakesh Pandharinath Marathe | Found Ok. | 10 | 20379356 - Ariwala Dhruval | Approved
757710 | 12/05/2025 | 1000140030 | 21034A | 1030 - Y-Piece Fit-up | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB160 | Shift A | 20077565 - Jaimin Patel | B (Expansion) | 20062365 - Chitranjan Bhikhabhai Patel | Found ok | 10 | 20077565 - Jaimin Patel | In Review
757744 | 12/05/2025 | 1000140321 | 21034B | 0100 - Hanger tube Cleaning WV | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BF050 | Shift A | 20379356 - Ariwala Dhruval | F | 20036852 - Manishkumar Bhatiya | Under cut and Uneven welding Found Corrected and Found ok. | 10 | 20379356 - Ariwala Dhruval | Approved
757711 | 12/05/2025 | 1000140030 | 21034A | 0880 - Attachment F/U and Welding | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB150 | Shift A | 20077565 - Jaimin Patel | B (Expansion) | 20076206 - Nikunjkumar maheshbhai Patel | Found ok | 10 | 20077565 - Jaimin Patel | In Review
757748 | 12/05/2025 | 1000139802 | 13022A | 0110 - Tube Bending on STB | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BF080 | Shift A | 20379356 - Ariwala Dhruval | F | 20036860 - Harshadkumar Jadav | Checked and Found Ok. | 10 | 20379356 - Ariwala Dhruval | Approved
757711 | 12/05/2025 | 1000140030 | 21034A | 0880 - Attachment F/U and Welding | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB150 | Shift A | 20077565 - Jaimin Patel | B (Expansion) | 20062400 - Pravinsinh Vijaysinh Gohil | Found ok | 10 | 20077565 - Jaimin Patel | In Review
757747 | 12/05/2025 | 1000139802 | 13022A | 0110 - Tube Bending on STB | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BF080 | Shift A | 20379356 - Ariwala Dhruval | F | 20054732 - Rahulbhai Jesangbhai Chaudhary | Checked and Found Ok. | 10 | 20379356 - Ariwala Dhruval | Approved
757712 | 12/05/2025 | 1000140030 | 21034A | 0900 - Distortion Correction | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB170 | Shift A | 20077565 - Jaimin Patel | B (Expansion) | 20059747 - Naga Bhupatbhai Dangar | Found ok | 10 | 20077565 - Jaimin Patel | In Review
757781 | 12/05/2025 | 1000140030 | 21034A | 0270 - Butt Joint Welding | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE015 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20076210 - Sannikumar Rajeshbhai Patel | No Observation. | 10 | 20098563 - Kalpeshkumar Patel | Approved
757712 | 12/05/2025 | 1000140030 | 21034A | 0900 - Distortion Correction | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB170 | Shift A | 20077565 - Jaimin Patel | B (Expansion) | 20093823 - Denish Dipakbhai Lad | Found ok | 10 | 20077565 - Jaimin Patel | In Review
757748 | 12/05/2025 | 1000139802 | 13022A | 0110 - Tube Bending on STB | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BF080 | Shift A | 20379356 - Ariwala Dhruval | F | 20063306 - Ankitkumar Rohitbhai Mevada | Checked and Found Ok. | 10 | 20379356 - Ariwala Dhruval | Approved
757713 | 12/05/2025 | 1000140030 | 21034A | 1040 - Y-Piece welding | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB240 | Shift B | 20077565 - Jaimin Patel | B (Expansion) | 20036777 - Patel Ronakkumar Anilbhai | Found ok | 10 | 20077565 - Jaimin Patel | In Review
757782 | 12/05/2025 | 1000140321 | 21034B | 0260 - Tube/Coil Butt Joint Fitup | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BE005 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20066509 - Jatinkumar Harshadbhai Patel | No Observation. | 10 | 20098563 - Kalpeshkumar Patel | Approved
757724 | 12/05/2025 | 1000140904 | 21034H | 0050 - MPM 20T WELDING -MPM1 | PANEL_LMB | 21034H-122000201 | SF21034H122000201L : DRG NO: 12200-0201L For 21034H | BC060 | Shift A | 20012636 - Chandan Jangid | C2 | 20085450 - Mukundkumar Pravinbhai Patel | Found ok |  | 20012636 - Chandan Jangid | In Review
757767 | 12/05/2025 | 1000139912 | 21034A | 0370 - Surface Visual, Weld visual | HEADERLMB | 21034A-151000101 | DU21034A1510101L-A : ECON. INLET HEADER | BA110 | Shift A | 20305091 - Solanki Dharmikkumar Kamleshbhai | A | 20081397 - Piyushkumar Viththalbhai Patel | Checked and found ok |  | 20305091 - Solanki Dharmikkumar Kamleshbhai | In Review
757719 | 12/05/2025 | 1000140904 | 21034H | 0040 - FIN CALIBRATION - 1 | PANEL_LMB | 21034H-122000201 | SF21034H122000201L : DRG NO: 12200-0201L For 21034H | BC058 | Shift A | 20012636 - Chandan Jangid | C2 | 20062434 - Kishankumar Damjibhai Vasava | Found ok |  | 20012636 - Chandan Jangid | In Review
757783 | 12/05/2025 | 1000140030 | 21034A | 0310 - Assembly Welding_Coils+Hanger tube | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20037224 - Upendra Rangpadiya | No Observation. |  | 20098563 - Kalpeshkumar Patel | Approved
757740 | 12/05/2025 | 1000140893 | 21034H | 0070 - Squeezing And Sizing | COIL_LMB | 21034H-152000101 | SF21034H152000101 : WBS :15200-0101 (ESL) for 21034H | BF040 | Shift A | 20379356 - Ariwala Dhruval | F | 20062395 - Nikulkumar Muljibhai Parmar | Found Ok. |  | 20379356 - Ariwala Dhruval | Approved
757783 | 12/05/2025 | 1000140030 | 21034A | 0310 - Assembly Welding_Coils+Hanger tube | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20036793 - Bhaveshbhai Khalasi | No Observation. |  | 20098563 - Kalpeshkumar Patel | Approved
757722 | 12/05/2025 | 1000140895 | 21034G | 0011 - AUTO TIG In Shop C | PANEL_LMB | 21034G-122000121 | SF21034G122000121L : DRG NO: 12200-0121L For 21034G | BC030 | Shift A | 20012636 - Chandan Jangid | C2 | 20043118 - Rohit Patel | Found ok |  | 20012636 - Chandan Jangid | In Review
757783 | 12/05/2025 | 1000140030 | 21034A | 0310 - Assembly Welding_Coils+Hanger tube | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20062723 - Gulabsinh Amarsinh Rathod | No Observation. |  | 20098563 - Kalpeshkumar Patel | Approved
757741 | 12/05/2025 | 1000140893 | 21034H | 0069 - ATCP | COIL_LMB | 21034H-152000101 | SF21034H152000101 : WBS :15200-0101 (ESL) for 21034H | BF060 | Shift A | 20379356 - Ariwala Dhruval | F | 20081400 - Jaimin Hasmukbhai Patel | Improper Cleaning Found. Increased Sec in System For Cleaning and Found Ok. |  | 20379356 - Ariwala Dhruval | Pending
757784 | 12/05/2025 | 1000140030 | 21034A | 0280 - Butt joint W/V-Distortion Correcti | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20054758 - Fatesang Bhailalbhai Parmar | During the sponge pass activity, some sponge pieces were found on floor, instructed to collect them and return them to store. |  | 20098563 - Kalpeshkumar Patel | Approved
757741 | 12/05/2025 | 1000140893 | 21034H | 0069 - ATCP | COIL_LMB | 21034H-152000101 | SF21034H152000101 : WBS :15200-0101 (ESL) for 21034H | BF060 | Shift A | 20379356 - Ariwala Dhruval | F | 20062398 - Maheshkumar Amratlal Makavana | Improper Cleaning Found. Increased Sec in System For Cleaning and Found Ok. |  | 20379356 - Ariwala Dhruval | Pending
757784 | 12/05/2025 | 1000140030 | 21034A | 0280 - Butt joint W/V-Distortion Correcti | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20041479 - Jaysukh Gohil | During the sponge pass activity, some sponge pieces were found on floor, instructed to collect them and return them to store. |  | 20098563 - Kalpeshkumar Patel | Approved
757742 | 12/05/2025 | 1000140750 | 21034G | 0050 - Tube Bending | COIL_LMB | 21034G-152000101 | SF21034G152000101 : WBS :15200-0101 (ESL) for 21034G | BF030 | Shift A | 20379356 - Ariwala Dhruval | F | 20049453 - Jigneshgiri Chelgiri Goswami | bend Checked and Found Ok. |  | 20379356 - Ariwala Dhruval | Approved
757785 | 12/05/2025 | 1000140030 | 21034A | 0300 - Assembly Fit Up _Coils+Hanger tube | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE045 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20034915 - Mohamed Shoeb Malek | On Assembly layout Tube cleaning done but not appropriate, informed and corrected. |  | 20098563 - Kalpeshkumar Patel | Approved
757742 | 12/05/2025 | 1000140750 | 21034G | 0050 - Tube Bending | COIL_LMB | 21034G-152000101 | SF21034G152000101 : WBS :15200-0101 (ESL) for 21034G | BF030 | Shift A | 20379356 - Ariwala Dhruval | F | 20063322 - Viralkumar Dharmendrabhai Bhandari | bend Checked and Found Ok. |  | 20379356 - Ariwala Dhruval | Approved
757784 | 12/05/2025 | 1000140030 | 21034A | 0280 - Butt joint W/V-Distortion Correcti | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20062994 - Harshadkumar Parsottambhai Prajapati | During the sponge pass activity, some sponge pieces were found on floor, instructed to collect them and return them to store. |  | 20098563 - Kalpeshkumar Patel | Approved
757742 | 12/05/2025 | 1000140750 | 21034G | 0050 - Tube Bending | COIL_LMB | 21034G-152000101 | SF21034G152000101 : WBS :15200-0101 (ESL) for 21034G | BF030 | Shift A | 20379356 - Ariwala Dhruval | F | 20063318 - Vivekkumar Rameshbhai Patel | bend Checked and Found Ok. |  | 20379356 - Ariwala Dhruval | Approved
757785 | 12/05/2025 | 1000140030 | 21034A | 0300 - Assembly Fit Up _Coils+Hanger tube | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE045 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20054046 - Hardik Manubhai Patel | On Assembly layout Tube cleaning done but not appropriate, informed and corrected. |  | 20098563 - Kalpeshkumar Patel | Approved
757745 | 12/05/2025 | 1000140893 | 21034H | 0020 - Marking and Cutting | COIL_LMB | 21034H-152000101 | SF21034H152000101 : WBS :15200-0101 (ESL) for 21034H | BF001 | Shift A | 20379356 - Ariwala Dhruval | F | 20064593 - Himanshukumar Rameshbhai Patel | Marking Checked and Found Ok. |  | 20379356 - Ariwala Dhruval | Pending
757791 | 12/05/2025 | 1000139802 | 13022A | 0750 - Assembly Fit Up | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BC100 | Shift A | 20012636 - Chandan Jangid | C2 | 20041305 - Jatinkumar Kumbhar | Found ok |  | 20012636 - Chandan Jangid | In Review
757742 | 12/05/2025 | 1000140750 | 21034G | 0050 - Tube Bending | COIL_LMB | 21034G-152000101 | SF21034G152000101 : WBS :15200-0101 (ESL) for 21034G | BF030 | Shift A | 20379356 - Ariwala Dhruval | F | 20064592 - Nimeshkumar Natvarbhai Patel | bend Checked and Found Ok. |  | 20379356 - Ariwala Dhruval | Approved
757786 | 12/05/2025 | 1000140030 | 21034A | 0270 - Butt Joint Welding | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE015 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20039814 - Mayur Padhiyar | Not Audited. |  | 20098563 - Kalpeshkumar Patel | In Review
757770 | 12/05/2025 | 1000140030 | 21034A | 0930 - Other Fabrication Activities | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB200 | Shift A | 20077565 - Jaimin Patel | B (Expansion) | 20066144 - Shirish Jagdishbhai Patel | Wrong drawing number found in identification punching. Informed to fitter and same was corrected on spot. |  | 20077565 - Jaimin Patel | In Review
757791 | 12/05/2025 | 1000139802 | 13022A | 0750 - Assembly Fit Up | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BC100 | Shift A | 20012636 - Chandan Jangid | C2 | 20059749 - Pravin Govabhai Chavda | Found ok |  | 20012636 - Chandan Jangid | In Review
757745 | 12/05/2025 | 1000140893 | 21034H | 0020 - Marking and Cutting | COIL_LMB | 21034H-152000101 | SF21034H152000101 : WBS :15200-0101 (ESL) for 21034H | BF001 | Shift A | 20379356 - Ariwala Dhruval | F | 20072923 - Dipakkumar Shivkumar Mishra | Marking Checked and Found Ok. |  | 20379356 - Ariwala Dhruval | Pending
757787 | 12/05/2025 | 30142 |  | 0070 - JIGS & FIXTURE |  |  | : | BZ995 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20090272 - Milankumar Bachubhai Bharavad | Fixture work was assigned. While performing assembly and flipping on stand, the end limb got stuck between the stand and distorted. Informed to modify the fixture to prevent distortion. |  | 20098563 - Kalpeshkumar Patel | Approved
757783 | 12/05/2025 | 1000140030 | 21034A | 0310 - Assembly Welding_Coils+Hanger tube | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20036774 - Rikinbhai Patel | No Observation. |  | 20098563 - Kalpeshkumar Patel | Approved
757794 | 12/05/2025 | 1000140321 | 21034B | 0800 - Tube/Coil Butt Joint Fitup | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD110 | Shift A | 20375639 - ONKAR GUPTA | D | 20059759 - Vishal Ranvirbhai Vainsh | Root face not made. Informed and corrected. |  | 20375639 - ONKAR GUPTA | Approved
757747 | 12/05/2025 | 1000139802 | 13022A | 0110 - Tube Bending on STB | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BF080 | Shift A | 20379356 - Ariwala Dhruval | F | 20054047 - Manojbahadur Krushnabahadur Thapa | Checked and Found Ok. |  | 20379356 - Ariwala Dhruval | Approved
757791 | 12/05/2025 | 1000139802 | 13022A | 0750 - Assembly Fit Up | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BC100 | Shift A | 20012636 - Chandan Jangid | C2 | 20051563 - Ankitkumar Babubhai Patel | Found ok |  | 20012636 - Chandan Jangid | In Review
757788 | 12/05/2025 | 30142 |  | 0070 - JIGS & FIXTURE |  |  | : | BZ995 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20038636 - Lakhmanbhai Kavad | Not Audited. |  | 20098563 - Kalpeshkumar Patel | Approved
757811 | 12/05/2025 | 1000140321 | 21034B | 0860 - Weld Visual/Cleaning/PT Point | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD180 | Shift A | 20375639 - ONKAR GUPTA | D | 20054037 - Harshadkumar Ganpatbhai Parmar | Found ok |  | 20375639 - ONKAR GUPTA | Approved
757771 | 12/05/2025 | 1000140030 | 21034A | 1070 - Marking and Cutting of Rod | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB010 | Shift A | 20077565 - Jaimin Patel | B (Expansion) | 20063328 - Nishantkumar Bharatbhai Panchal | Found ok |  | 20077565 - Jaimin Patel | In Review
757794 | 12/05/2025 | 1000140321 | 21034B | 0800 - Tube/Coil Butt Joint Fitup | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD110 | Shift A | 20375639 - ONKAR GUPTA | D | 20062383 - Keyurkumar Ramabhai Patel | Root face not made. Informed and corrected. |  | 20375639 - ONKAR GUPTA | Approved
757789 | 12/05/2025 | 30142 |  | 0060 - WORKED FOR OTHER DEPARTMENT |  |  | : | BZ995 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20063859 - Jentibhai Mathurbhai Rathwa | No Observation. |  | 20098563 - Kalpeshkumar Patel | Approved
757818 | 12/05/2025 | 1000140616 | 21034B | 0220 - Stub Fit-up | HEADERLMB | 21034B-151002101 | DU21034B1512101L-A : ECON. INLET HEADER | BA030 | Shift A | 20305091 - Solanki Dharmikkumar Kamleshbhai | A | 20090264 - Subhash Santosh Jadav | Checked and found ok |  | 20305091 - Solanki Dharmikkumar Kamleshbhai | In Review
757783 | 12/05/2025 | 1000140030 | 21034A | 0310 - Assembly Welding_Coils+Hanger tube | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20041306 - Devidkumar Patel | No Observation. |  | 20098563 - Kalpeshkumar Patel | Approved
757797 | 12/05/2025 | 1000140321 | 21034B | 0820 - Butt joint W/V-Distortion Correcti | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD120 | Shift A | 20375639 - ONKAR GUPTA | D | 20091319 - Ajaybhai Babubhai Rathwa | Found ok |  | 20375639 - ONKAR GUPTA | Approved
757789 | 12/05/2025 | 30142 |  | 0060 - WORKED FOR OTHER DEPARTMENT |  |  | : | BZ995 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20091321 - Nitinkumar Govindbhai Parmar | No Observation. |  | 20098563 - Kalpeshkumar Patel | Approved
757820 | 12/05/2025 | 1000140617 | 21034B | 0250 - Stub welding | HEADERLMB | 21034B-151002101 | DU21034B1512101L-B : ECON. INLET HEADER | BA120 | Shift A | 20305091 - Solanki Dharmikkumar Kamleshbhai | A | 20036841 - Arvindkumar Himasiya | Checked and found ok |  | 20305091 - Solanki Dharmikkumar Kamleshbhai | In Review
757785 | 12/05/2025 | 1000140030 | 21034A | 0300 - Assembly Fit Up _Coils+Hanger tube | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE045 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20054017 - Jigarkumar Jasavantlal Patel | On Assembly layout Tube cleaning done but not appropriate, informed and corrected. |  | 20098563 - Kalpeshkumar Patel | Approved
757801 | 12/05/2025 | 1000140321 | 21034B | 0860 - Weld Visual/Cleaning/PT Point | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD180 | Shift A | 20375639 - ONKAR GUPTA | D | 20090878 - Ravindrakumar Kanubhai Solanki | Found ok |  | 20375639 - ONKAR GUPTA | Approved
757795 | 12/05/2025 | 1000140321 | 21034B | 0810 - Butt Joint Welding | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD190 | Shift A | 20375639 - ONKAR GUPTA | D | 20019442 - Kirtisinh Rana | Crater point not merged. Informed and corrected. |  | 20375639 - ONKAR GUPTA | Approved
757824 | 12/05/2025 | 1000139789 | 13022B | 0770 - Weld Visual/Cleaning/PT Point | COIL_LMB | 13022B-PD70WB09145 | DU13022BPD70914501 : LP EVAP-2 COILS WITH SUPPORT PLATE | BC100 | Shift A | 20012636 - Chandan Jangid | C2 | 20062403 - Ayajuddin Iliyasbhai Shekh | Visual point not attended properly so informed to fabricator and point attended |  | 20012636 - Chandan Jangid | In Review
757785 | 12/05/2025 | 1000140030 | 21034A | 0300 - Assembly Fit Up _Coils+Hanger tube | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE045 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20064597 - Sumit Chandramohan Povle | On Assembly layout Tube cleaning done but not appropriate, informed and corrected. |  | 20098563 - Kalpeshkumar Patel | Approved
757816 | 12/05/2025 | 1000139912 | 21034A | 0220 - Stub Fit-up | HEADERLMB | 21034A-151000101 | DU21034A1510101L-A : ECON. INLET HEADER | BA030 | Shift A | 20305091 - Solanki Dharmikkumar Kamleshbhai | A | 20064279 - Satishkumar Ganpatbhai Patel | during stub fit up project number Mismatch found after information mismatch corrected. |  | 20305091 - Solanki Dharmikkumar Kamleshbhai | Approved
757799 | 12/05/2025 | 1000140321 | 21034B | 0860 - Weld Visual/Cleaning/PT Point | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD180 | Shift A | 20375639 - ONKAR GUPTA | D | 20074618 - Jayesh Timbadiya | Found ok |  | 20375639 - ONKAR GUPTA | Approved
757825 | 12/05/2025 | 1000139802 | 13022A | 0750 - Assembly Fit Up | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BC100 | Shift A | 20012636 - Chandan Jangid | C2 | 20061602 - Jayeshbhai Khushalbhai Patel | Found ok |  | 20012636 - Chandan Jangid | Pending
757787 | 12/05/2025 | 30142 |  | 0070 - JIGS & FIXTURE |  |  | : | BZ995 | Shift A | 20098563 - Kalpeshkumar Patel | E | 20064596 - Shaileshkumar Manilal Patel | Fixture work was assigned. While performing assembly and flipping on stand, the end limb got stuck between the stand and distorted. Informed to modify the fixture to prevent distortion. |  | 20098563 - Kalpeshkumar Patel | Approved
757818 | 12/05/2025 | 1000140616 | 21034B | 0220 - Stub Fit-up | HEADERLMB | 21034B-151002101 | DU21034B1512101L-A : ECON. INLET HEADER | BA030 | Shift A | 20305091 - Solanki Dharmikkumar Kamleshbhai | A | 20072904 - Jenish Vijaybhai Patel | Checked and found ok |  | 20305091 - Solanki Dharmikkumar Kamleshbhai | In Review
757803 | 12/05/2025 | 1000140321 | 21034B | 0860 - Weld Visual/Cleaning/PT Point | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD180 | Shift A | 20375639 - ONKAR GUPTA | D | 20066148 - Niteshkumar Parbhubhai Patel | Found ok |  | 20375639 - ONKAR GUPTA | Approved
757826 | 12/05/2025 | 1000140908 | HAZIRA-DO | 0020 - Cutting,Grinding & EP | STRUCTURA | MNMBF3-67504 | DUBF350419B/TB-1D : BF#3 - TIE BEAM-B/TB-1D | BA010 | Shift A | 20305091 - Solanki Dharmikkumar Kamleshbhai | A | 20049458 - Tusharbhai Devabhai Prajapati | Checked and found ok |  | 20305091 - Solanki Dharmikkumar Kamleshbhai | In Review
757790 | 12/05/2025 | 1000139802 | 13022A | 0750 - Assembly Fit Up | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BC100 | Shift A | 20012636 - Chandan Jangid | C2 | 20048294 - Virendrakumar Mokariya | Found ok |  | 20012636 - Chandan Jangid | In Review
757831 | 12/05/2025 | 1000140030 | 21034A | 0880 - Attachment F/U and Welding | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB150 | Shift B | 20098561 - Vijaykumar Patel | B (Expansion) | 20076204 - Naresh Jadavbhai Chauhan | Found ok |  | 20098561 - Vijaykumar Patel | Approved
757804 | 12/05/2025 | 1000140321 | 21034B | 0860 - Weld Visual/Cleaning/PT Point | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD180 | Shift A | 20375639 - ONKAR GUPTA | D | 20062391 - Parth Chandrakant Patel | Crater point not merged. Informed and corrected. |  | 20375639 - ONKAR GUPTA | Approved
757832 | 12/05/2025 | 1000140030 | 21034A | 1000 - Assembly Fit Up_Block | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB150 | Shift B | 20098561 - Vijaykumar Patel | B (Expansion) | 20076378 - Harishbhai Malabhai Nalwaya | Found ok |  | 20098561 - Vijaykumar Patel | Approved
757791 | 12/05/2025 | 1000139802 | 13022A | 0750 - Assembly Fit Up | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BC100 | Shift A | 20012636 - Chandan Jangid | C2 | 20036843 - Virendra Khandivar | Found ok |  | 20012636 - Chandan Jangid | In Review
757835 | 12/05/2025 | 1000140030 | 21034A | 1030 - Y-Piece Fit-up | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB160 | Shift B | 20098561 - Vijaykumar Patel | B (Expansion) | 20054016 - Devendrabhai Amarsang Patel | Found ok |  | 20098561 - Vijaykumar Patel | Approved
757811 | 12/05/2025 | 1000140321 | 21034B | 0860 - Weld Visual/Cleaning/PT Point | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD180 | Shift A | 20375639 - ONKAR GUPTA | D | 20041307 - Vijaykumar Modi | Found ok |  | 20375639 - ONKAR GUPTA | Approved
757833 | 12/05/2025 | 1000140030 | 21034A | 0870 - FABRICATION PROCESS AFTER PWHT | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB130 | Shift B | 20098561 - Vijaykumar Patel | B (Expansion) | 20066754 - Anilkumar Pravinbhai Rohit | Found ok |  | 20098561 - Vijaykumar Patel | Approved
757791 | 12/05/2025 | 1000139802 | 13022A | 0750 - Assembly Fit Up | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BC100 | Shift A | 20012636 - Chandan Jangid | C2 | 20118747 - Ganga Savadas Bharada | Found ok |  | 20012636 - Chandan Jangid | In Review
757839 | 12/05/2025 | 1000140810 | 13022A | 0020 - Marking and Cutting Tubes | COIL_LMB | 13022A-PD30WB09156 | DU13022APD309156Z4 : TUBE NO.12 - O.D. 44.5 x 3.25 THK. | BA010 | Shift B | 20375625 - DHIRAJ DUDESHWAR BAWANKULE | A | 20040274 - Rakeshkumar Bhoi | found ok |  | 20375625 - DHIRAJ DUDESHWAR BAWANKULE | In Review
757811 | 12/05/2025 | 1000140321 | 21034B | 0860 - Weld Visual/Cleaning/PT Point | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD180 | Shift A | 20375639 - ONKAR GUPTA | D | 20085454 - Niraj Pravinbhai Patel | Found ok |  | 20375639 - ONKAR GUPTA | Approved
757834 | 12/05/2025 | 1000140030 | 21034A | 1040 - Y-Piece welding | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB240 | Shift B | 20098561 - Vijaykumar Patel | B (Expansion) | 20040650 - Sandip Patel | Found ok |  | 20098561 - Vijaykumar Patel | Approved
757797 | 12/05/2025 | 1000140321 | 21034B | 0820 - Butt joint W/V-Distortion Correcti | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD120 | Shift A | 20375639 - ONKAR GUPTA | D | 20019428 - Sunilkumar | Found ok |  | 20375639 - ONKAR GUPTA | Approved
757846 | 12/05/2025 | 1000140365 | 1724 | 0150 - Weld Visual & inspection | PIPINGLMB | 1724-NTTD04-13400 | DU17242169667-0040 : PSH DESUPERHEATER | BB045 | Shift B | 20375637 - SHLOK YADAV | B | 20062358 - Jaydeep Rameshbhai Rajani | Visual point given and they corrected it. |  | 20375637 - SHLOK YADAV | Approved
757814 | 12/05/2025 | 1000140710 | 21034B | 0060 - Tube Bending R 150 | COIL_LMB | 21034B-142002152 | SF21034B142002152 : WBS :14200-2152 (1ry RH Terminal) for 21 | BD020 | Shift A | 20375639 - ONKAR GUPTA | D | 20090879 - Anupkumar Anilbhai Patel | Found ok |  | 20375639 - ONKAR GUPTA | Approved
757835 | 12/05/2025 | 1000140030 | 21034A | 1030 - Y-Piece Fit-up | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB160 | Shift B | 20098561 - Vijaykumar Patel | B (Expansion) | 20066158 - Jayminbhai Rameshchandra Machhi | Found ok |  | 20098561 - Vijaykumar Patel | Approved
757797 | 12/05/2025 | 1000140321 | 21034B | 0820 - Butt joint W/V-Distortion Correcti | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD120 | Shift A | 20375639 - ONKAR GUPTA | D | 20054038 - Satishkumar Babubhai Patel | Found ok |  | 20375639 - ONKAR GUPTA | Approved
757847 | 12/05/2025 | 1000140359 | 1724 | 0100 - Welding of Reinforcing Pad | PIPINGLMB | 1724-NTKG05-13400 | DU1724M4411321117 : LINER PIPE | BB030 | Shift B | 20375637 - SHLOK YADAV | B | 20019435 - Anis | check and found ok |  | 20375637 - SHLOK YADAV | Approved
757831 | 12/05/2025 | 1000140030 | 21034A | 0880 - Attachment F/U and Welding | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB150 | Shift B | 20098561 - Vijaykumar Patel | B (Expansion) | 20076205 - Vijay Dattubhai Luhar | Found ok |  | 20098561 - Vijaykumar Patel | Approved
757846 | 12/05/2025 | 1000140365 | 1724 | 0150 - Weld Visual & inspection | PIPINGLMB | 1724-NTTD04-13400 | DU17242169667-0040 : PSH DESUPERHEATER | BB045 | Shift B | 20375637 - SHLOK YADAV | B | 20076449 - Manojkumar Bharatsinh Parmar | Visual point given and they corrected it. |  | 20375637 - SHLOK YADAV | Approved
757811 | 12/05/2025 | 1000140321 | 21034B | 0860 - Weld Visual/Cleaning/PT Point | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD180 | Shift A | 20375639 - ONKAR GUPTA | D | 20091320 - Jigneshkumar Maheshbhai Patel | Found ok |  | 20375639 - ONKAR GUPTA | Approved
757849 | 12/05/2025 | 1000140533 | HAZIRA-DO | 0090 - Drilling by Portable machine | STRUCTURA | MNMBF3-67517 | DUBF36751705RBR-8 : BF#3 - RAFTER BRACING-RBR-8 | BB030 | Shift B | 20375637 - SHLOK YADAV | B | 20090880 - Ranjitbhai Rameshbhai Rathod | Drill Dia and chips cleaning check found ok |  | 20375637 - SHLOK YADAV | Approved
757834 | 12/05/2025 | 1000140030 | 21034A | 1040 - Y-Piece welding | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB240 | Shift B | 20098561 - Vijaykumar Patel | B (Expansion) | 20024569 - Shailendrakumar Patel | Found ok |  | 20098561 - Vijaykumar Patel | Approved
757850 | 12/05/2025 | 1000141327 | HAZIRA-DO | 0020 - Cutting,Grinding & EP | STRUCTURA | MNMBF3-67509 | SFMNM6750925FLMAYB : Floor Beam-Shop B(0525) | BB010 | Shift B | 20375637 - SHLOK YADAV | B | 20064282 - Rajnish Vasrambhai Sonagara | check and found ok |  | 20375637 - SHLOK YADAV | Approved
757814 | 12/05/2025 | 1000140710 | 21034B | 0060 - Tube Bending R 150 | COIL_LMB | 21034B-142002152 | SF21034B142002152 : WBS :14200-2152 (1ry RH Terminal) for 21 | BD020 | Shift A | 20375639 - ONKAR GUPTA | D | 20029849 - Khumansinh Vaghela | Found ok |  | 20375639 - ONKAR GUPTA | Approved
757851 | 12/05/2025 | 1000141327 | HAZIRA-DO | 0010 - Marking | STRUCTURA | MNMBF3-67509 | SFMNM6750925FLMAYB : Floor Beam-Shop B(0525) | BB010 | Shift B | 20375637 - SHLOK YADAV | B | 20072912 - Prakash Jasubhai Makwana | punching detail check and found ok |  | 20375637 - SHLOK YADAV | Approved
757839 | 12/05/2025 | 1000140810 | 13022A | 0020 - Marking and Cutting Tubes | COIL_LMB | 13022A-PD30WB09156 | DU13022APD309156Z4 : TUBE NO.12 - O.D. 44.5 x 3.25 THK. | BA010 | Shift B | 20375625 - DHIRAJ DUDESHWAR BAWANKULE | A | 20076380 - Harshadkumar Kantilal Joshi | found ok |  | 20375625 - DHIRAJ DUDESHWAR BAWANKULE | In Review
757857 | 12/05/2025 | 1000140321 | 21034B | 0270 - Butt Joint Welding | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BE015 | Shift B | 20047728 - Jitendra Gadaria | E | 20021442 - Jayeshkumar Patel | FOUND OK |  | 20047728 - Jitendra Gadaria | In Review
757816 | 12/05/2025 | 1000139912 | 21034A | 0220 - Stub Fit-up | HEADERLMB | 21034A-151000101 | DU21034A1510101L-A : ECON. INLET HEADER | BA030 | Shift A | 20305091 - Solanki Dharmikkumar Kamleshbhai | A | 20049455 - Chetan Mansukhbhai Patel | during stub fit up project number Mismatch found after information mismatch corrected. |  | 20305091 - Solanki Dharmikkumar Kamleshbhai | Approved
757859 | 12/05/2025 | 1000140321 | 21034B | 0260 - Tube/Coil Butt Joint Fitup | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BE005 | Shift B | 20047728 - Jitendra Gadaria | E | 20051622 - Jaydipsinh Somsinh Chauhan | FOUND DIFFERENT MARK NO. IN A COIL SO INFORM TO WORKMEN AND CORRECTED SAME AS |  | 20047728 - Jitendra Gadaria | In Review
757856 | 12/05/2025 | 1000140801 | 13022A | 0050 - Tube Bending | COIL_LMB | 13022A-PD30WB09129 | DU13022APD309129Z3 : TUBE NO.11 - O.D. 44.5 x 3.25 THK. | BA070 | Shift B | 20375625 - DHIRAJ DUDESHWAR BAWANKULE | A | 20059741 - Hajibhai Ismalbhai Malek | found ok |  | 20375625 - DHIRAJ DUDESHWAR BAWANKULE | Approved
757859 | 12/05/2025 | 1000140321 | 21034B | 0260 - Tube/Coil Butt Joint Fitup | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BE005 | Shift B | 20047728 - Jitendra Gadaria | E | 20054745 - Amitkumar Nanubhai Patel | FOUND DIFFERENT MARK NO. IN A COIL SO INFORM TO WORKMEN AND CORRECTED SAME AS |  | 20047728 - Jitendra Gadaria | In Review
757820 | 12/05/2025 | 1000140617 | 21034B | 0250 - Stub welding | HEADERLMB | 21034B-151002101 | DU21034B1512101L-B : ECON. INLET HEADER | BA120 | Shift A | 20305091 - Solanki Dharmikkumar Kamleshbhai | A | 20020610 - Shriyamkumar Patel | Checked and found ok |  | 20305091 - Solanki Dharmikkumar Kamleshbhai | In Review
757859 | 12/05/2025 | 1000140321 | 21034B | 0260 - Tube/Coil Butt Joint Fitup | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BE005 | Shift B | 20047728 - Jitendra Gadaria | E | 20063311 - Prashantkumar Govindbhai Ramani | FOUND DIFFERENT MARK NO. IN A COIL SO INFORM TO WORKMEN AND CORRECTED SAME AS |  | 20047728 - Jitendra Gadaria | In Review
757858 | 12/05/2025 | 1000140321 | 21034B | 0270 - Butt Joint Welding | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BE015 | Shift B | 20047728 - Jitendra Gadaria | E | 20076209 - Dhavalkumar Vitthalbhai Prajapati | NO OBSERVATION |  | 20047728 - Jitendra Gadaria | In Review
757863 | 12/05/2025 | 1000140030 | 21034A | 0400 - TPI Inspection and work | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE120 | Shift B | 20047728 - Jitendra Gadaria | E | 20041919 - Nilesh Patel | NO OBSERVATION |  | 20047728 - Jitendra Gadaria | In Review
757826 | 12/05/2025 | 1000140908 | HAZIRA-DO | 0020 - Cutting,Grinding & EP | STRUCTURA | MNMBF3-67504 | DUBF350419B/TB-1D : BF#3 - TIE BEAM-B/TB-1D | BA010 | Shift A | 20305091 - Solanki Dharmikkumar Kamleshbhai | A | 20064585 - Kishorkumar Natvarbhai Chauhan | Checked and found ok |  | 20305091 - Solanki Dharmikkumar Kamleshbhai | In Review
757861 | 12/05/2025 | 1000140690 | 1725 | 0160 - Tube Bending R 225 | COIL_LMB | 1725-APTR01-14200 | SF1725APTR0114200 : WBS :14200-0201 (Tiroda) for 1725-APTR01 | BE030 | Shift B | 20047728 - Jitendra Gadaria | E | 20040570 - Maheshbhai Vasava | tube surface found ok . |  | 20047728 - Jitendra Gadaria | In Review
757859 | 12/05/2025 | 1000140321 | 21034B | 0260 - Tube/Coil Butt Joint Fitup | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BE005 | Shift B | 20047728 - Jitendra Gadaria | E | 20072921 - Hitesh Pravinbhai Patel | FOUND DIFFERENT MARK NO. IN A COIL SO INFORM TO WORKMEN AND CORRECTED SAME AS |  | 20047728 - Jitendra Gadaria | In Review
757864 | 12/05/2025 | 1000140030 | 21034A | 0310 - Assembly Welding_Coils+Hanger tube | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift B | 20047728 - Jitendra Gadaria | E | 20063310 - Mayankkumar Arvindbhai Patel | Informed to maintain parameter strictly as tube thickness is low. |  | 20047728 - Jitendra Gadaria | In Review
757832 | 12/05/2025 | 1000140030 | 21034A | 1000 - Assembly Fit Up_Block | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB150 | Shift B | 20098561 - Vijaykumar Patel | B (Expansion) | 20041480 - Kishankumar Barad | Found ok |  | 20098561 - Vijaykumar Patel | Approved
757862 | 12/05/2025 | 1000140750 | 21034G | 0320 - Tube Bending R127 | COIL_LMB | 21034G-152000101 | SF21034G152000101 : WBS :15200-0101 (ESL) for 21034G | BE030 | Shift B | 20047728 - Jitendra Gadaria | E | 20036848 - Anilkumar Patel | tube surface found ok . |  | 20047728 - Jitendra Gadaria | In Review
757860 | 12/05/2025 | 1000140689 | 1725 | 0110 - Machining on lathe | COIL_LMB | 1725-APKW01-14200 | SF1725APKW0114200 : WBS :14200-0201 (Kawai) for 1725-APKW01 | BE002 | Shift B | 20047728 - Jitendra Gadaria | E | 20063327 - Mitesh Bharatbhai Mehta | FOUND OK |  | 20047728 - Jitendra Gadaria | In Review
757865 | 12/05/2025 | 1000140030 | 21034A | 0310 - Assembly Welding_Coils+Hanger tube | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift B | 20047728 - Jitendra Gadaria | E | 20029847 - Mayur Patel | FOUND OK |  | 20047728 - Jitendra Gadaria | In Review
757833 | 12/05/2025 | 1000140030 | 21034A | 0870 - FABRICATION PROCESS AFTER PWHT | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB130 | Shift B | 20098561 - Vijaykumar Patel | B (Expansion) | 20051565 - Nimeshkumar Vishnubhai Patel | Found ok |  | 20098561 - Vijaykumar Patel | Approved
757862 | 12/05/2025 | 1000140750 | 21034G | 0320 - Tube Bending R127 | COIL_LMB | 21034G-152000101 | SF21034G152000101 : WBS :15200-0101 (ESL) for 21034G | BE030 | Shift B | 20047728 - Jitendra Gadaria | E | 20066752 - Vasantkumar Chhanabhai Parmar | tube surface found ok . |  | 20047728 - Jitendra Gadaria | In Review
757861 | 12/05/2025 | 1000140690 | 1725 | 0160 - Tube Bending R 225 | COIL_LMB | 1725-APTR01-14200 | SF1725APTR0114200 : WBS :14200-0201 (Tiroda) for 1725-APTR01 | BE030 | Shift B | 20047728 - Jitendra Gadaria | E | 20019554 - Ketankumar Mevada | tube surface found ok . |  | 20047728 - Jitendra Gadaria | In Review
757867 | 12/05/2025 | 1000140030 | 21034A | 0320 - Weld Visual/Cleaning/PT Point | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift B | 20047728 - Jitendra Gadaria | E | 20059752 - Ghanshyam Shankarbhai Bavliya | SOME CRATER NOT MERGE PROPERLY, SAME CORRECTED |  | 20047728 - Jitendra Gadaria | In Review
757838 | 12/05/2025 | 1000140810 | 13022A | 0020 - Marking and Cutting Tubes | COIL_LMB | 13022A-PD30WB09156 | DU13022APD309156Z4 : TUBE NO.12 - O.D. 44.5 x 3.25 THK. | BA010 | Shift B | 20375625 - DHIRAJ DUDESHWAR BAWANKULE | A | 20062350 - Umangkumar Kantilal Patel | found ok |  | 20375625 - DHIRAJ DUDESHWAR BAWANKULE | In Review
757870 | 12/05/2025 | 1000140030 | 21034A | 0320 - Weld Visual/Cleaning/PT Point | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift B | 20047728 - Jitendra Gadaria | E | 20076213 - Chetanbhai Thakorbhai Patel | Not Audited. |  | 20047728 - Jitendra Gadaria | In Review
757861 | 12/05/2025 | 1000140690 | 1725 | 0160 - Tube Bending R 225 | COIL_LMB | 1725-APTR01-14200 | SF1725APTR0114200 : WBS :14200-0201 (Tiroda) for 1725-APTR01 | BE030 | Shift B | 20047728 - Jitendra Gadaria | E | 20066322 - Vishnu Bharat Tandel | tube surface found ok . |  | 20047728 - Jitendra Gadaria | In Review
757869 | 12/05/2025 | 1000140030 | 21034A | 1060 - Spacer Rework | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift B | 20047728 - Jitendra Gadaria | E | 20049372 - Pankajkumar Kantibhai Padhiyar | NO OBSERVATION |  | 20047728 - Jitendra Gadaria | In Review
757838 | 12/05/2025 | 1000140810 | 13022A | 0020 - Marking and Cutting Tubes | COIL_LMB | 13022A-PD30WB09156 | DU13022APD309156Z4 : TUBE NO.12 - O.D. 44.5 x 3.25 THK. | BA010 | Shift B | 20375625 - DHIRAJ DUDESHWAR BAWANKULE | A | 20062382 - Jigar Babulal Patel | found ok |  | 20375625 - DHIRAJ DUDESHWAR BAWANKULE | In Review
757872 | 12/05/2025 | 1000140321 | 21034B | 0300 - Assembly Fit Up _Coils+Hanger tube | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BE045 | Shift B | 20047728 - Jitendra Gadaria | E | 20063857 - Yatinkumar Manubhai Parmar | Stopper cleaning not found proper, same informed and corrected. |  | 20047728 - Jitendra Gadaria | In Review
757862 | 12/05/2025 | 1000140750 | 21034G | 0320 - Tube Bending R127 | COIL_LMB | 21034G-152000101 | SF21034G152000101 : WBS :15200-0101 (ESL) for 21034G | BE030 | Shift B | 20047728 - Jitendra Gadaria | E | 20063854 - Rakeshbhai Nathabhai Pargi | tube surface found ok . |  | 20047728 - Jitendra Gadaria | In Review
757873 | 12/05/2025 | 1000140030 | 21034A | 0280 - Butt joint W/V-Distortion Correcti | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift B | 20047728 - Jitendra Gadaria | E | 20019424 - Sehulbhai | FOUND OK |  | 20047728 - Jitendra Gadaria | In Review
757850 | 12/05/2025 | 1000141327 | HAZIRA-DO | 0020 - Cutting,Grinding & EP | STRUCTURA | MNMBF3-67509 | SFMNM6750925FLMAYB : Floor Beam-Shop B(0525) | BB010 | Shift B | 20375637 - SHLOK YADAV | B | 20064594 - Dasharathji Ishvarji Solanki | check and found ok |  | 20375637 - SHLOK YADAV | Approved
757880 | 12/05/2025 | 1000140911 | HAZIRA-DO | 0050 - Shaft Fit up | STRUCTURA | MNMBF3-67517 | DUBF36751705RB-6-2 : BF#3 - RAFTER BEAM-RB-6-Part B | BA030 | Shift B | 20012616 - Ramnarayan Kumawat | A | 20062439 - Jaydeepbhai Haribhai Gohil | found ok |  | 20012616 - Ramnarayan Kumawat | Approved
757863 | 12/05/2025 | 1000140030 | 21034A | 0400 - TPI Inspection and work | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE120 | Shift B | 20047728 - Jitendra Gadaria | E | 20062405 - Khumabhai Savdasbhai Rabari | NO OBSERVATION |  | 20047728 - Jitendra Gadaria | In Review
757894 | 12/05/2025 | 1000140893 | 21034H | 0050 - Tube Bending | COIL_LMB | 21034H-152000101 | SF21034H152000101 : WBS :15200-0101 (ESL) for 21034H | BF030 | Shift B | 20375631 - APURBA NAG | F | 20049378 - Ronak Ishwarbhai Parekh | OVALITY CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review
757852 | 12/05/2025 | 1000141327 | HAZIRA-DO | 0020 - Cutting,Grinding & EP | STRUCTURA | MNMBF3-67509 | SFMNM6750925FLMAYB : Floor Beam-Shop B(0525) | BB010 | Shift B | 20375637 - SHLOK YADAV | B | 20040279 - Tarunkumar Patel | check and found ok |  | 20375637 - SHLOK YADAV | Approved
757884 | 12/05/2025 | 1000140616 | 21034B | 0270 - Header End Plate & Nozzle end | HEADERLMB | 21034B-151002101 | DU21034B1512101L-A : ECON. INLET HEADER | BA030 | Shift B | 20012616 - Ramnarayan Kumawat | A | 20021340 - Maheshkumar Tandel | found ok |  | 20012616 - Ramnarayan Kumawat | Approved
757865 | 12/05/2025 | 1000140030 | 21034A | 0310 - Assembly Welding_Coils+Hanger tube | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift B | 20047728 - Jitendra Gadaria | E | 20021439 - Hardikkumar Tandel | FOUND OK |  | 20047728 - Jitendra Gadaria | In Review
757894 | 12/05/2025 | 1000140893 | 21034H | 0050 - Tube Bending | COIL_LMB | 21034H-152000101 | SF21034H152000101 : WBS :15200-0101 (ESL) for 21034H | BF030 | Shift B | 20375631 - APURBA NAG | F | 20063313 - SANJAYKUMAR JAYANTIBHAI SUTARIA | OVALITY CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review
757856 | 12/05/2025 | 1000140801 | 13022A | 0050 - Tube Bending | COIL_LMB | 13022A-PD30WB09129 | DU13022APD309129Z3 : TUBE NO.11 - O.D. 44.5 x 3.25 THK. | BA070 | Shift B | 20375625 - DHIRAJ DUDESHWAR BAWANKULE | A | 20063847 - Gauravkumar Amrutbhai Patel | found ok |  | 20375625 - DHIRAJ DUDESHWAR BAWANKULE | Approved
757886 | 12/05/2025 | 1000139913 | 21034A | 0250 - Stub welding | HEADERLMB | 21034A-151000101 | DU21034A1510101L-B : ECON. INLET HEADER | BA120 | Shift B | 20012616 - Ramnarayan Kumawat | A | 20041430 - Alpeshkumar Parmar | found ok |  | 20012616 - Ramnarayan Kumawat | Approved
757868 | 12/05/2025 | 1000140030 | 21034A | 1060 - Spacer Rework | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift B | 20047728 - Jitendra Gadaria | E | 20090274 - Vaibhavkumar Ambalal Patel | Spacer Rework assigned to them, on some spacer cut marks found on spacer, informed to take care while grinding. |  | 20047728 - Jitendra Gadaria | In Review
757894 | 12/05/2025 | 1000140893 | 21034H | 0050 - Tube Bending | COIL_LMB | 21034H-152000101 | SF21034H152000101 : WBS :15200-0101 (ESL) for 21034H | BF030 | Shift B | 20375631 - APURBA NAG | F | 20085455 - Mihirkumar Bhikabhai Patel | OVALITY CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review
757859 | 12/05/2025 | 1000140321 | 21034B | 0260 - Tube/Coil Butt Joint Fitup | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BE005 | Shift B | 20047728 - Jitendra Gadaria | E | 20051535 - Darshankumar Chandrakantbhai Mistry | FOUND DIFFERENT MARK NO. IN A COIL SO INFORM TO WORKMEN AND CORRECTED SAME AS |  | 20047728 - Jitendra Gadaria | In Review
757895 | 12/05/2025 | 1000139802 | 13022A | 0110 - Tube Bending on STB | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BF080 | Shift B | 20375631 - APURBA NAG | F | 20021444 - Nikhilkumar Bhatt | CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review
757871 | 12/05/2025 | 1000140321 | 21034B | 0300 - Assembly Fit Up _Coils+Hanger tube | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BE045 | Shift B | 20047728 - Jitendra Gadaria | E | 20036854 - Maheshkumar Tank | Stopper cleaning not found proper, same informed and corrected. |  | 20047728 - Jitendra Gadaria | In Review
757900 | 12/05/2025 | 1000140893 | 21034H | 0700 - Butt Joint (Auto-Tig) | COIL_LMB | 21034H-152000101 | SF21034H152000101 : WBS :15200-0101 (ESL) for 21034H | BF070 | Shift B | 20375631 - APURBA NAG | F | 20116776 - Ajitsinh Shivsinh Solanki | CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review
757862 | 12/05/2025 | 1000140750 | 21034G | 0320 - Tube Bending R127 | COIL_LMB | 21034G-152000101 | SF21034G152000101 : WBS :15200-0101 (ESL) for 21034G | BE030 | Shift B | 20047728 - Jitendra Gadaria | E | 20019440 - Manishbhai | tube surface found ok . |  | 20047728 - Jitendra Gadaria | In Review
757897 | 12/05/2025 | 1000139802 | 13022A | 0080 - Butt Joint (Auto-Tig) | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BF070 | Shift B | 20375631 - APURBA NAG | F | 20064587 - Urvesh Bhadreshbhai Patel | CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review
757873 | 12/05/2025 | 1000140030 | 21034A | 0280 - Butt joint W/V-Distortion Correcti | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift B | 20047728 - Jitendra Gadaria | E | 20054741 - Sanjaykumar Damjibhai Vasava | FOUND OK |  | 20047728 - Jitendra Gadaria | In Review
757902 | 12/05/2025 | 1000139891 | 13021A | 0060 - ATCP | COIL_LMB | 13021A-PD70WB09702 | DU13021APD70970201 : LP EVAP-2 & LP SH COILS WITH SUPPORT PLA | BF060 | Shift B | 20375631 - APURBA NAG | F | 20063321 - Chirag Parsottamdas Prajapati | checked the length of the tubes and found ok |  | 20375631 - APURBA NAG | In Review
757864 | 12/05/2025 | 1000140030 | 21034A | 0310 - Assembly Welding_Coils+Hanger tube | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift B | 20047728 - Jitendra Gadaria | E | 20116764 - Niravkumar Shashikant Tailor | Informed to maintain parameter strictly as tube thickness is low. |  | 20047728 - Jitendra Gadaria | In Review
757902 | 12/05/2025 | 1000139891 | 13021A | 0060 - ATCP | COIL_LMB | 13021A-PD70WB09702 | DU13021APD70970201 : LP EVAP-2 & LP SH COILS WITH SUPPORT PLA | BF060 | Shift B | 20375631 - APURBA NAG | F | 20063319 - Vijaykumar Pravinchandra Pandya | checked the length of the tubes and found ok |  | 20375631 - APURBA NAG | In Review
757880 | 12/05/2025 | 1000140911 | HAZIRA-DO | 0050 - Shaft Fit up | STRUCTURA | MNMBF3-67517 | DUBF36751705RB-6-2 : BF#3 - RAFTER BEAM-RB-6-Part B | BA030 | Shift B | 20012616 - Ramnarayan Kumawat | A | 20066503 - Mehulkumar Sureshbhai Varia | found ok |  | 20012616 - Ramnarayan Kumawat | Approved
757903 | 12/05/2025 | 1000140321 | 21034B | 0800 - Tube/Coil Butt Joint Fitup | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD110 | Shift B | 20375626 - MONU KUMAR | D | 20051512 - Alpeshkumar Jethabhai Nagariya | EP Chips found on layout informed and corrected |  | 20375626 - MONU KUMAR | In Review
757866 | 12/05/2025 | 1000140030 | 21034A | 0320 - Weld Visual/Cleaning/PT Point | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift B | 20047728 - Jitendra Gadaria | E | 20054769 - Navinkumar Khushalji Sankhla | On Some portion of female spacer locking found excess, informed to not to weld excess welding on sliding spacers. |  | 20047728 - Jitendra Gadaria | In Review
757904 | 12/05/2025 | 1000140710 | 21034B | 0060 - Tube Bending R 150 | COIL_LMB | 21034B-142002152 | SF21034B142002152 : WBS :14200-2152 (1ry RH Terminal) for 21 | BD020 | Shift B | 20375626 - MONU KUMAR | D | 20063341 - Jigarbhai Jagdishbhai Khalasi | Found ok |  | 20375626 - MONU KUMAR | Pending
757887 | 12/05/2025 | 1000139912 | 21034A | 0230 - ROOT WELDING | HEADERLMB | 21034A-151000101 | DU21034A1510101L-A : ECON. INLET HEADER | BA120 | Shift B | 20012616 - Ramnarayan Kumawat | A | 20040649 - Rakeshkumar Chaudhari | found ok |  | 20012616 - Ramnarayan Kumawat | Approved
757903 | 12/05/2025 | 1000140321 | 21034B | 0800 - Tube/Coil Butt Joint Fitup | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD110 | Shift B | 20375626 - MONU KUMAR | D | 20066147 - Mayur Dharamshibhai Vadhrodiya | EP Chips found on layout informed and corrected |  | 20375626 - MONU KUMAR | In Review
757873 | 12/05/2025 | 1000140030 | 21034A | 0280 - Butt joint W/V-Distortion Correcti | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift B | 20047728 - Jitendra Gadaria | E | 20067068 - Priyank Shaileshkumar Trivedi | FOUND OK |  | 20047728 - Jitendra Gadaria | In Review
757918 | 12/05/2025 | 1000140321 | 21034B | 0840 - Assembly Fit Up | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD100 | Shift B | 20375626 - MONU KUMAR | D | 20085294 - Pankajkumar Dalpatbhai Parmar | found ok |  | 20375626 - MONU KUMAR | Pending
757894 | 12/05/2025 | 1000140893 | 21034H | 0050 - Tube Bending | COIL_LMB | 21034H-152000101 | SF21034H152000101 : WBS :15200-0101 (ESL) for 21034H | BF030 | Shift B | 20375631 - APURBA NAG | F | 20076381 - Vimalkumar Champakbhai Patel | OVALITY CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review
757907 | 12/05/2025 | 30143 |  | 0060 - WORKED FOR OTHER DEPARTMENT |  |  | : | BZ994 | Shift B | 20375631 - APURBA NAG | F | 20040575 - Sumitbhai Rami | NOT AUDITED |  | 20375631 - APURBA NAG | In Review
757874 | 12/05/2025 | 1000140030 | 21034A | 0310 - Assembly Welding_Coils+Hanger tube | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BE050 | Shift B | 20047728 - Jitendra Gadaria | E | 20040574 - Hirenkumar Patel | FOUND OK |  | 20047728 - Jitendra Gadaria | In Review
757932 | 12/05/2025 | 1000139802 | 13022A | 0750 - Assembly Fit Up | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BC100 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20066324 - Kamlesh Dhaneshbhai Mistry | Found ok |  | 20007029 - Dharmesh Kumar Rana | In Review
757895 | 12/05/2025 | 1000139802 | 13022A | 0110 - Tube Bending on STB | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BF080 | Shift B | 20375631 - APURBA NAG | F | 20064588 - Nimeshbhai Girishbhai Patel | CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review
757918 | 12/05/2025 | 1000140321 | 21034B | 0840 - Assembly Fit Up | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD100 | Shift B | 20375626 - MONU KUMAR | D | 20063850 - Nehalkumar Subhashbhai Patel | found ok |  | 20375626 - MONU KUMAR | Pending
757878 | 12/05/2025 | 1000140908 | HAZIRA-DO | 0120 - Assembly Fit-up | STRUCTURA | MNMBF3-67504 | DUBF350419B/TB-1D : BF#3 - TIE BEAM-B/TB-1D | BA030 | Shift B | 20012616 - Ramnarayan Kumawat | A | 20064842 - Prafulbhai Rameshbhai Munjpara | found ok |  | 20012616 - Ramnarayan Kumawat | Approved
757932 | 12/05/2025 | 1000139802 | 13022A | 0750 - Assembly Fit Up | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BC100 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20067354 - Riteshkumar Harshadbhai Patel | Found ok |  | 20007029 - Dharmesh Kumar Rana | In Review
757898 | 12/05/2025 | 1000140893 | 21034H | 0070 - Squeezing And Sizing | COIL_LMB | 21034H-152000101 | SF21034H152000101 : WBS :15200-0101 (ESL) for 21034H | BF040 | Shift B | 20375631 - APURBA NAG | F | 20048301 - Pravin Suva | CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | Approved
757925 | 12/05/2025 | 1000140321 | 21034B | 0810 - Butt Joint Welding | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD190 | Shift B | 20375626 - MONU KUMAR | D | 20021419 - Bharatbhai Parmar | found ok |  | 20375626 - MONU KUMAR | In Review
757883 | 12/05/2025 | 1000140616 | 21034B | 0230 - ROOT WELDING | HEADERLMB | 21034B-151002101 | DU21034B1512101L-A : ECON. INLET HEADER | BA120 | Shift B | 20012616 - Ramnarayan Kumawat | A | 20036788 - Umeshbhai Prajapati | found ok |  | 20012616 - Ramnarayan Kumawat | Approved
757935 | 12/05/2025 | 1000140904 | 21034H | 0060 - MPM 8T WELDING - MPM2 | PANEL_LMB | 21034H-122000201 | SF21034H122000201L : DRG NO: 12200-0201L For 21034H | BC061 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20066508 - Pratapbhai Vinubhai Makwana | Found ok |  | 20007029 - Dharmesh Kumar Rana | In Review
757901 | 12/05/2025 | 1000140321 | 21034B | 0100 - Hanger tube Cleaning WV | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BF050 | Shift B | 20375631 - APURBA NAG | F | 20029848 - Nilaykumar Prajapati | CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review
757929 | 12/05/2025 | 1000139789 | 13022B | 0770 - Weld Visual/Cleaning/PT Point | COIL_LMB | 13022B-PD70WB09145 | DU13022BPD70914501 : LP EVAP-2 COILS WITH SUPPORT PLATE | BC100 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20072913 - Hardikkumar Ratilal Patel | Found ok. |  | 20007029 - Dharmesh Kumar Rana | In Review
757896 | 12/05/2025 | 1000139802 | 13022A | 0080 - Butt Joint (Auto-Tig) | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BF070 | Shift B | 20375631 - APURBA NAG | F | 20054747 - Dhavalkumar Bharatbhai Patel | CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review
757935 | 12/05/2025 | 1000140904 | 21034H | 0060 - MPM 8T WELDING - MPM2 | PANEL_LMB | 21034H-122000201 | SF21034H122000201L : DRG NO: 12200-0201L For 21034H | BC061 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20072915 - Chiragkumar Kundrambhai Natali | Found ok |  | 20007029 - Dharmesh Kumar Rana | In Review
757903 | 12/05/2025 | 1000140321 | 21034B | 0800 - Tube/Coil Butt Joint Fitup | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD110 | Shift B | 20375626 - MONU KUMAR | D | 20059808 - Ranmal Nagshi Gadhavi | EP Chips found on layout informed and corrected |  | 20375626 - MONU KUMAR | In Review
757931 | 12/05/2025 | 1000139802 | 13022A | 0270 - Layout For Butt joint Fit Up | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BF005 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20116760 - Jayeshbhai Rameshbhai Zapadiya | Found ok |  | 20007029 - Dharmesh Kumar Rana | Pending
757898 | 12/05/2025 | 1000140893 | 21034H | 0070 - Squeezing And Sizing | COIL_LMB | 21034H-152000101 | SF21034H152000101 : WBS :15200-0101 (ESL) for 21034H | BF040 | Shift B | 20375631 - APURBA NAG | F | 20063332 - Vishalkumar Kantibhai Nayee | CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | Approved
757936 | 12/05/2025 | 1000140904 | 21034H | 0040 - FIN CALIBRATION - 1 | PANEL_LMB | 21034H-122000201 | SF21034H122000201L : DRG NO: 12200-0201L For 21034H | BC058 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20072914 - Harjibhai Parshottambhai Raval | Found ok |  | 20007029 - Dharmesh Kumar Rana | In Review
757903 | 12/05/2025 | 1000140321 | 21034B | 0800 - Tube/Coil Butt Joint Fitup | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD110 | Shift B | 20375626 - MONU KUMAR | D | 20059811 - Ankush Jaysukhbhai Dhorajiya | EP Chips found on layout informed and corrected |  | 20375626 - MONU KUMAR | In Review
757932 | 12/05/2025 | 1000139802 | 13022A | 0750 - Assembly Fit Up | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BC100 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20061607 - Hardipsinh Dilipsinh Raj | Found ok |  | 20007029 - Dharmesh Kumar Rana | In Review
757899 | 12/05/2025 | 1000139802 | 13022A | 0110 - Tube Bending on STB | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BF080 | Shift B | 20375631 - APURBA NAG | F | 20036853 - Dharmeshkumar Mochi | CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review
757939 | 12/05/2025 | 1000140895 | 21034G | 0012 - BUTT JOINT GRINDING | PANEL_LMB | 21034G-122000121 | SF21034G122000121L : DRG NO: 12200-0121L For 21034G | BC150 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20063855 - Amitkumar Ratilal Parmar | Butt joint not grinded properly and polishing not done. Feedback given for the same |  | 20007029 - Dharmesh Kumar Rana | In Review
757904 | 12/05/2025 | 1000140710 | 21034B | 0060 - Tube Bending R 150 | COIL_LMB | 21034B-142002152 | SF21034B142002152 : WBS :14200-2152 (1ry RH Terminal) for 21 | BD020 | Shift B | 20375626 - MONU KUMAR | D | 20062441 - Keyurkumar Vinodbhai Patel | Found ok |  | 20375626 - MONU KUMAR | Pending
757937 | 12/05/2025 | 1000140904 | 21034H | 0050 - MPM 20T WELDING -MPM1 | PANEL_LMB | 21034H-122000201 | SF21034H122000201L : DRG NO: 12200-0201L For 21034H | BC060 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20063340 - Bhushanbhai Mohanbhai Igale | Found ok |  | 20007029 - Dharmesh Kumar Rana | In Review
757899 | 12/05/2025 | 1000139802 | 13022A | 0110 - Tube Bending on STB | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BF080 | Shift B | 20375631 - APURBA NAG | F | 20063316 - Dipakkumar Dineshbhai Chudasama | CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review
757942 | 12/05/2025 | 1000140904 | 21034H | 0010 - Shot Blasting of tubes | PANEL_LMB | 21034H-122000201 | SF21034H122000201L : DRG NO: 12200-0201L For 21034H | BC010 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20062409 - Amitkumar Kantilal Mistry | After tube blasting, partial identification missed. Same informed and rectified. |  | 20007029 - Dharmesh Kumar Rana | In Review
757918 | 12/05/2025 | 1000140321 | 21034B | 0840 - Assembly Fit Up | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD100 | Shift B | 20375626 - MONU KUMAR | D | 20085452 - Vishal Rasiklal Pithwa | found ok |  | 20375626 - MONU KUMAR | Pending
757945 | 12/05/2025 | 1000140321 | 21034B | 0780 - Rework Hours (STB bend correction) | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD100 | Shift B | 20026676 - Chiragkumar Prajapati | D | 20059760 - Poorveshkumar Rameshchandra Zalavadia | Found ok |  | 20026676 - Chiragkumar Prajapati | In Review
757901 | 12/05/2025 | 1000140321 | 21034B | 0100 - Hanger tube Cleaning WV | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BF050 | Shift B | 20375631 - APURBA NAG | F | 20076215 - Haresh Hira Bharda | CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review
757948 | 12/05/2025 | 1000140321 | 21034B | 0800 - Tube/Coil Butt Joint Fitup | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD110 | Shift B | 20026676 - Chiragkumar Prajapati | D | 20085291 - Tejmalji Ranchhodji Thakor | Butt joint offset fit up, informed and corrected. |  | 20026676 - Chiragkumar Prajapati | In Review
757925 | 12/05/2025 | 1000140321 | 21034B | 0810 - Butt Joint Welding | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD190 | Shift B | 20375626 - MONU KUMAR | D | 20040280 - Virajsinh Raj | found ok |  | 20375626 - MONU KUMAR | In Review
757954 | 12/05/2025 | 1000140750 | 21034G | 0070 - Squeezing And Sizing | COIL_LMB | 21034G-152000101 | SF21034G152000101 : WBS :15200-0101 (ESL) for 21034G | BF040 | Shift B | 20375631 - APURBA NAG | F | 20048301 - Pravin Suva | CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review
757906 | 12/05/2025 | 1000140030 | 21034A | 0880 - Attachment F/U and Welding | COIL_LMB | 21034A-142000101 | SF21034A142000101 : WBS :14200-0101 (1ry RH) for 21034A | BB150 | Shift B | 20098561 - Vijaykumar Patel | B (Expansion) | 20072908 - Vinod Devidas Patil | Found ok |  | 20098561 - Vijaykumar Patel | Approved
757957 | 12/05/2025 | 1000140750 | 21034G | 0070 - Squeezing And Sizing | COIL_LMB | 21034G-152000101 | SF21034G152000101 : WBS :15200-0101 (ESL) for 21034G | BF040 | Shift C | 20047725 - Parth Patel | F | 20054755 - Hirenkumar Kishorbhai Patel | Checked & found ok. |  | 20047725 - Parth Patel | In Review
757931 | 12/05/2025 | 1000139802 | 13022A | 0270 - Layout For Butt joint Fit Up | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BF005 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20142310 - Vijaybhai Shanubhai Rathod | Found ok |  | 20007029 - Dharmesh Kumar Rana | Pending
757920 | 12/05/2025 | 1000140321 | 21034B | 0860 - Weld Visual/Cleaning/PT Point | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD180 | Shift B | 20375626 - MONU KUMAR | D | 20091322 - Akshay Shantilal Patel | Merging points was not done properly informed and corrected |  | 20375626 - MONU KUMAR | Pending
757932 | 12/05/2025 | 1000139802 | 13022A | 0750 - Assembly Fit Up | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BC100 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20063336 - Arjunbhai Ashokbhai Patil | Found ok |  | 20007029 - Dharmesh Kumar Rana | In Review
757928 | 12/05/2025 | 1000139789 | 13022B | 0760 - Assembly Welding | COIL_LMB | 13022B-PD70WB09145 | DU13022BPD70914501 : LP EVAP-2 COILS WITH SUPPORT PLATE | BC100 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20036786 - Aashukumar Khalasi | Arc strike generated during welding on tube area. Feedback given for the same. |  | 20007029 - Dharmesh Kumar Rana | Approved
757937 | 12/05/2025 | 1000140904 | 21034H | 0050 - MPM 20T WELDING -MPM1 | PANEL_LMB | 21034H-122000201 | SF21034H122000201L : DRG NO: 12200-0201L For 21034H | BC060 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20051568 - Pankajkumar Manoharbhai Chitte | Found ok |  | 20007029 - Dharmesh Kumar Rana | In Review
757928 | 12/05/2025 | 1000139789 | 13022B | 0760 - Assembly Welding | COIL_LMB | 13022B-PD70WB09145 | DU13022BPD70914501 : LP EVAP-2 COILS WITH SUPPORT PLATE | BC100 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20076202 - Vikramsinh Ranjitsinh Sindha | Arc strike generated during welding on tube area. Feedback given for the same. |  | 20007029 - Dharmesh Kumar Rana | Approved
757939 | 12/05/2025 | 1000140895 | 21034G | 0012 - BUTT JOINT GRINDING | PANEL_LMB | 21034G-122000121 | SF21034G122000121L : DRG NO: 12200-0121L For 21034G | BC150 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20059748 - Niyazmahmad Hushen Badi | Butt joint not grinded properly and polishing not done. Feedback given for the same |  | 20007029 - Dharmesh Kumar Rana | In Review
757930 | 12/05/2025 | 1000139789 | 13022B | 0770 - Weld Visual/Cleaning/PT Point | COIL_LMB | 13022B-PD70WB09145 | DU13022BPD70914501 : LP EVAP-2 COILS WITH SUPPORT PLATE | BC100 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20066141 - Milankumar Rameshbhai Zalavadia | Arc strike left during self-visual at 3 locations. Same informed and rectified. |  | 20007029 - Dharmesh Kumar Rana | In Review
757940 | 12/05/2025 | 1000140895 | 21034G | 0011 - AUTO TIG In Shop C | PANEL_LMB | 21034G-122000121 | SF21034G122000121L : DRG NO: 12200-0121L For 21034G | BC030 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20054752 - Sagarkumar Champakbhai Khalasi | Found ok |  | 20007029 - Dharmesh Kumar Rana | In Review
757932 | 12/05/2025 | 1000139802 | 13022A | 0750 - Assembly Fit Up | COIL_LMB | 13022A-PD30WB09129 | DU13022APD30912901 : HP EVAP-1 COILS WITH SUPPORT PLATE | BC100 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20062407 - Ranjitbhai Chaturbhai Parmar | Found ok |  | 20007029 - Dharmesh Kumar Rana | In Review
757944 | 12/05/2025 | 1000140321 | 21034B | 0810 - Butt Joint Welding | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD190 | Shift B | 20026676 - Chiragkumar Prajapati | D | 20019479 - Nileshkumar Patel | Found ok |  | 20026676 - Chiragkumar Prajapati | Pending
757933 | 12/05/2025 | 1000139789 | 13022B | 0760 - Assembly Welding | COIL_LMB | 13022B-PD70WB09145 | DU13022BPD70914501 : LP EVAP-2 COILS WITH SUPPORT PLATE | BC100 | Shift B | 20007029 - Dharmesh Kumar Rana | C2 | 20116770 - Laljibhai Shantilal Jadav | Found ok |  | 20007029 - Dharmesh Kumar Rana | In Review
757957 | 12/05/2025 | 1000140750 | 21034G | 0070 - Squeezing And Sizing | COIL_LMB | 21034G-152000101 | SF21034G152000101 : WBS :15200-0101 (ESL) for 21034G | BF040 | Shift C | 20047725 - Parth Patel | F | 20064840 - Harshkumar Naginbhai Surati | Checked & found ok. |  | 20047725 - Parth Patel | In Review
757945 | 12/05/2025 | 1000140321 | 21034B | 0780 - Rework Hours (STB bend correction) | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD100 | Shift B | 20026676 - Chiragkumar Prajapati | D | 20049460 - Vasudev Baldevdas Sadhu | Found ok |  | 20026676 - Chiragkumar Prajapati | In Review
757948 | 12/05/2025 | 1000140321 | 21034B | 0800 - Tube/Coil Butt Joint Fitup | COIL_LMB | 21034B-142002101 | SF21034B142002101 : WBS :14200-2101 (1ry RH) for 21034B | BD110 | Shift B | 20026676 - Chiragkumar Prajapati | D | 20048289 - Nikunjkumar Kachhiya | Butt joint offset fit up, informed and corrected. |  | 20026676 - Chiragkumar Prajapati | In Review
757954 | 12/05/2025 | 1000140750 | 21034G | 0070 - Squeezing And Sizing | COIL_LMB | 21034G-152000101 | SF21034G152000101 : WBS :15200-0101 (ESL) for 21034G | BF040 | Shift B | 20375631 - APURBA NAG | F | 20063332 - Vishalkumar Kantibhai Nayee | CHECKED AND FOUND OK |  | 20375631 - APURBA NAG | In Review